**Section 871.202 Stop-Work Order**

a) The Agency may, for any violation of this Part, by written order to the grantee, require the grantee to stop all or any part of the project work for a period of not more than 30 days after the date of the order, and for any further period to which the parties may agree. Any such order shall be specifically identified as a stop-work order issued pursuant to this Section. Any such order shall include a list of the project activities to which the stop-work order shall apply. Upon receipt of such an order, the grantee shall forthwith comply with its terms and take all reasonable steps to minimize the incurrence of costs allocable to the work covered by the order during the period of work stoppage. Within a period of not more than 30 days of the date of the stop-work order, or within any extension of that period to which the parties shall have agreed, the Agency shall either:

1) Cancel the stop-work order upon the resolution of the violations leading to that stop-work order; or

2) Terminate the work covered by such order as provided in Section 871.203 of this Part.

b) If a stop-work order issued under this condition is canceled or the period of the order or any extension there of expires, the grantee shall resume work. An equitable adjustment shall be made in the grant period, the project period, or grant amount, or all of these, and the grant instrument shall be amended accordingly, if:

1) The stop-work order results either in an increase in the time required to complete the project, or an increase in the grantee's cost properly allocable to the performance of any part of the project; and

2) The grantee asserts a written claim for such adjustment within 30 days after the end of the period of work stoppage. Such claim must be submitted prior to final payment under the grant.

c) Costs incurred by the grantee after the receipt of a stop-work order, or within any extension of the stop-work order period to which the Agency and the grantee shall have agreed, shall be allowable costs only if so defined by Section 871.601 of this Part.

(Source: Amended at 19 Ill. Reg. 11871, effective August 3, 1995)